## Ark1
|  |  | Project Start | [17 empty] | Project End
[5 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3
|  | Time (Days): | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
Task | Assignee | Duration
Initial Meeting | Project Manager | 2 Hours | bar: 1; Week 1 6; Week 2 13; Week 3 20
Identifying Goals & Research | Project Manager Content Developer | 2 Days | bar: 1 to 2; Week 1 6; Week 2 13; Week 3 20
Strategic & Content Planning | Project Manager Content Developer | 2 Days | bar: Week 1 3 to Week 1 4; Week 1 6; Week 2 13; Week 3 20
Photoshoot | Photographer | 1 Day | bar: Week 1 4; Week 1 6; Week 2 13; Week 3 20
Styletiles | Designer | 1 Day | bar: Week 1 5 to Week 1 6; Week 2 13; Week 3 20
Wireframes | Designer | 1 Day | bar: Week 1 6; Week 1 8; Week 2 13; Week 3 20
UI/UX planning & coding | Developer & Designer | 1 Day | bar: Week 1 6; Week 1 9; Week 2 13; Week 3 20
Site Build | Developer | 3 Days | bar: Week 2 10 to Week 2 12
Optimization for different breakpoints | Developer | 3 Days | bar: Week 2 12; Week 2 15 to Week 2 16
Copyright Managment | Copywriter | 1 Day | bar: Week 3 17
Refinement & Bugfixes | Developer | 3 Days | bar: Week 3 17 to Week 3 19